## Sheet2
Si se asigna el proyecto a un tercero externo, también se asignan las responsabilidades cotidianas de dirección del proyecto. Sin embargo, la empresa aun necesita tener un nivel de involucramiento para validar que el proyecto se está conduciendo adecuadamente y que el prestador de servicios podrá entregar los productos o servicios de acuerdo con las expectativas de la organización. Esto requiere que el prestador de servicios proporcione información significativa y retroalimentación proactiva respecto al estado del proyecto. También es necersario que la organización contratante se sienta confortable con los procesos que serán usados por el proveedor para dirigir el proyecto.
El aseguramiento de calidad se refiere a los procesos usados para gestionar el proyecto e integrar los entregables. (En contraste con el control de calidad, el cuál se refiere a las actividades para crear los entregables), Dado que no se es responsable de la creación de entregables (control de calidad), se debe asegurar que el proveedor use prácticas "sanas" (Aseguramiento de calidad), para dirigir el proyecto y crear los entregables.
Esta lista de verificación para el Aseguramiento de Calidad de proyectos "outsourceados" contiene los criterios necesarios para revisar:
Que los acuerdos iniciales contienen información necesaria para gestionar las relaciónes subsecuentes, Esto es que dichos acuerdos contengan That the up-front agreements contain the information necessary to subsequently manage the relationship. For instance, if you want periodic reporting, you need to make sure it is included in the Project Definition or contract. If you want to validate that interim deliverables are acceptable to your company, you need to agree on completeness and correctness criteria ahead of time.
That the project is proceeding on track and that you know about any deviations from plan. These ongoing questions can be validated at scheduled times, or at previously agreed up project milestones.
That the project concludes as you expect based on the Project Definition and contract.
This checklist contains the basic questions to ask and what to look for. It should be supplemented with questions that are specific to your project and your contract with the outsourcer. If either party in the contract makes any agreements or commitments, they should be added to this checklist so that they can be monitored throughout the project.
Note:
This checklist picks up when the project has already been defined and the outsourcer has been chosen. It should not be used to define the project or pick the outsourcer.
This checklist assumes that you are outsourcing a project, such as an IT development project. This checklist will not work if you are outsourcing a department or a service. For instance, if you are outsourcing your ongoing help desk services, this checklist will not be applicable.
The assumption for the checklist is that a Project Definition was created, along with a formal contract. (Your company may have a different term for the Project Definition, such as project charter or statement of work.) If this planning document is not prepared and formally approved, the information on the checklist needs to be a part of the contract. (Remove this comment section from final document.)

## Sheet1
Beginning of the Project |  | Y/N
Project Definition
Has a Project Definition (or similar document) been prepared by your company or the outsourcer?
Has the project scope been clearly defined, including a description of every final deliverable to be produced?
Have any areas out of scope been clearly documented?
Have expectations been agreed to for the level of quality of the deliverables, including completeness and correctness criteria?
Have overall project costs been documented and agreed to?
Have firm deadline dates been agreed to and confirmed?
Has systems, user, and code documentation been included as deliverables?
Have training needs been addressed as deliverables?
Has a Project Definition been approved in writing by the appropriate stakeholders and managers at your company and the outsourcer?
Has a comprehensive project workplan been created by the outsourcer? (Your company does not need to approve it. Just validate that it exists and is reasonable.)
Project Management Procedures
Does the outsourcer have clear procedures in place for managing issues, scope, and risk?
Is your company clear on what its role is in the management of issues, scope, and risk?
Does the outsourcer have a process in place to manage overall quality?
Do your company and the outsourcer have an agreement on the level and frequency of formal communication that is expected during the project?
Has the vendor been clear on what resources they need from your company and when they will be needed?
Have turnover procedures been established and agreed to?
Have a number of milestones been established to review progress so far and validate the project is on track for completion?
Contract
Is there a contractual agreement that spells out the expectations of both parties in terms of deliverables to be produced, deadlines, payment schedule, completeness and correctness criteria, etc?
Does the contract describe a process for amending the agreement in the future?
Does the contract state the consequences for the outsourcer of failing to meet deadline or quality expectations?
If interim payments are expected, is the contract clear on when they will be made, and what expectations need to be achieved for the interim payment to be made?
Are appropriate security and nondisclosure statements included in the contract?
Are appropriate code ownership and property rights included in the contract?
Has the contract been prepared, reviewed, and approved by your legal department?
Has the contract been formally signed by your sponsor, the outsourcer, and any other appropriate parties?
Any questions that have been answered “no” should be pursued and explained. Usually this is a sign that there is cause for concern. The more questions that are answered “no,” the more potential trouble the project is in. Work with the outsourcer to explain the reason for the “no” answer, and determine what can be done to remedy the situation. (Remove this comment section from final document.)
Ongoing Questions |  | Y/N
Validate at Key Milestones
Project Management
Can the vendor clearly explain where the project is vs. where it should be at this time?
Is the outsourcer following their procedures for managing issues, scope, risk, quality, etc.?
Are issues being resolved in a timely manner?
Are scope change requests being managed, and is the sponsor formally approving changes?
Are risks being identified and managed successfully?
Is communication between the outsourcer and your company occurring as agreed to?
Should the contract or Project Definition be updated to reflect any major changes to the project?
Is your company clear on what resources are required to assist the outsourcer in the completion of the project?
Deliverables
Have the deliverables specified in the Project Definition and the contract been completed up to this point?
Will all the future deliverables specified in the Project Definition be completed on time and within budget?
Have all deliverables from the outsourcer been formally approved based on adherence to the agreed upon completeness and correctness criteria?
Contract
If interim payments are expected, has the outsourcer completed all required work up to this point — to the agreed upon level of quality?
Have all terms and conditions of the contract been satisfied as expected for this point in the project?
Should the contract or Project Definition be updated to reflect any major changes to the project?
Any questions that have been answered “no” should be pursued and explained. Usually this is a sign that there is cause for concern. The more questions that are answered “no,” the more potential trouble the project is in. Work with the outsourcer to explain the reason for the “no” answer, and determine what can be done to remedy the situation. (Remove this comment section from final document.)